## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status | Date
1 | 1 |  | Understand and Collect Contract/Aggrement data |  | 0 | Nidhi | completed | 2025-09-12
2 | 2 |  | Learn Basis Concepts of AI (LLM, Embeddings, vector store, RAG) |  | 0 | Nidhi | completed | 2025-09-18
3 | 3 |  | Use LLMs for contract analysis. |  | 2 | Nidhi | completed | 2025-09-24
4 | 4 |  | Clause Identification using Large Language Model |  | 3 | Nidhi | completed | 2025-09-26
5 | 5 |  | Store template data into Database |  | 4 | Nidhi | completed | 2025-09-30
6 | 6 |  | Risk assessment algorithm that flags potential compliance issues based on regulatory standards and suggests amendments |  | 5 | Nidhi | completed | 2025-10-03
7 | 7 |  | UI integration in the project (take input and show result) |  | 6 | Nidhi | completed | 2025-10-07
8 | 8 |  | Set up the environment for data collection (e.g., scraping tools). |  | 0 | Nidhi | completed | 2025-10-10
9 | 9 |  | Integrate APIs that track legal changes (e.g., GDPR updates). |  | 6 | Nidhi | completed | 2025-10-14
10 | 10 |  | Automatically applies relevant updates to active contracts. |  | 9 | Nidhi | completed | 2025-10-14
11 | 11 |  | Provide real-time notifications about compliance status |  | 6 | Nidhi | completed | 2025-10-16
12 | 12 |  | Test the notification system by sending alerts based on detected compliance issues or updates. |  | 11 | Nidhi | completed | 2025-10-21
|  |  | Create presentation on the Project (ppt) |  |  | Nidhi | Completed | 2025-10-30

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7